## Sheet1
Task No. | Task Allotted Date | Project Code | Project | Task Description | Task Allotted to | Alloted days | Submission Date for Manager review | Major Review/Comments by Manager (Yes or No) | Review Completion date | Date of Actual Completion of Task | Task completed Day | Task Status | Delay in task completion | Rating | Project No | Projects | Staff | Delay in task completion | Rating
1 | 2025-12-18 | 150 | Khokhra NH58 DPR | Time Limit proposal | Zulfi | 15 | 2026-01-31 | No | 2026-01-31 | 2026-02-02 | 46 | Completed | 31 | 1 | 96 | NH8C DPR | Zulfi | <=0 | 5
2 | 2025-12-25 | 310 | Palanpur DPR | Preparation of Draft DPR (All volumes) | Zulfi | 30 | 2026-01-31 | No | 2026-01-31 | 2026-02-02 | 39 | Completed | 9 | 2 | 111 | Kerala NH766 DPR | Govardhan | 1-3 | 4
3 | 2026-01-02 | 310 | Palanpur DPR | Preparation of Draft DPR (All volumes) | Zulfi | 30 | 2026-01-31 | No | 2026-01-31 | 2026-02-02 | 31 | Completed | 1 | 4 | 124 | Katargam GIDC | Toshit | 4-6 | 3
4 | [14 empty] | 148 | Pardi Kaprada NH848 DPR | Shyam | 7-9 | 2
5 | [14 empty] | 150 | Khokhra NH58 DPR | Aasim | >=10 | 1
6 | [14 empty] | 157 | Daman DPR | Prabhiksha
7 | [14 empty] | 205 | Dholera DPR | Yashshvini
8 | [14 empty] | 244 | Savli GIDC DPR | Aum
9 | [14 empty] | 248 | RE Park DPR | Anish
10 | [14 empty] | 261 | VUDA TP-22 PMC | Bhautik
[15 empty] | 301 | Rajpipla DPR | Viren
[15 empty] | 310 | Palanpur DPR
[15 empty] | -- | Vagra GIDC -PIP DPR
[15 empty] | 318 | VUDA Ring Road PMC
[15 empty] | 326 | Andhra NH216 PMC
[15 empty] | 329 | Coimbatore DPR
[15 empty] | 335 | BAUDA - Zhagadiya PMC
[15 empty] | 338 | Madurai DPR
[15 empty] | 383 | NH8C -Flyover DPR
[15 empty] | 361 | Nagaland PMC
[15 empty] | 369 | Sachin DPR
[15 empty] | 377 | Navsari DPR
[15 empty] | 376 | Vadodara - SOU DPR
[15 empty] | 396 | Assam NH427 PMC
[15 empty] | 397 | Ankleshwar-Rajpipla HSC
[15 empty] | 414 | Porbandar DPR
[15 empty] | 415 | Amod-Dahej DPR
[15 empty] | 416 | VUDA Flyover PMC
[15 empty] | 417 | PMC NH329A
[15 empty] | 418 | VUDA Green Road PMC
[15 empty] | 419 | VUDA ROB PMC
[15 empty] | 420 | Surat SER
[15 empty] | 421 | NH-64 DPR

## Sheet2
Staff | Completed Task | Pending Task | Average Rating
Zulfi | 3 | 0 | #DIV/0!
Govardhan | 0 | 0 | #DIV/0!
Toshit | 0 | 0 | #DIV/0!
Shyam | 0 | 0 | #DIV/0!
Aasim | 0 | 0 | #DIV/0!
Prabhiksha | 0 | 0 | #DIV/0!
Yashshvini | 0 | 0 | #DIV/0!
Aum | 0 | 0 | #DIV/0!
Anish | 0 | 0 | #DIV/0!
Bhautik | 0 | 0 | #DIV/0!
Viren | 0 | 0 | #DIV/0!