## DPR Stage ....Date (hidden)
DETAILED PROJECT REPORT (DPR) ACTIVITY SCHEDULE
Sr No. | Activity Description | Reference | Volume | Annexure | Status of activity | Estimated or Actual Date of Completion
1 | Draft / Final Inception Report incl. QAP |  |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | Reconnaissance Survey
| Collection of Exisitng Road details e.g. CW width Details, Builtup areas Detail, Junctions details (e.g. Types, Width, Category etc..) | - | - | - | - | -
Collection of Exisitng CD Structure, Bridges & Structures details (e.g. Types, Size, Span etc..)
► | Subnission & Approval
| Prepration & Submission of Draft Inception Report incl. QAP | - | - | - |  | -
| Comments from Concern approval authority & Its Compliance, if any | - | - | - |  | -
| Approval of Draft Inception Report incl. QAP | - | - | - |  | -
| Prepration & Submission of Final Inception Report incl. QAP | - | - | - |  | -
| RA Bill (On submission of Final Inception Report incl. QAP) | - | - | - |  | -
| Approval of Final Inception Report incl. QAP | - | - | - |  | -
2 | Draft Feasibility Report |  |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Reconnaissance Survey
| Existing Road Inventory & Pavement Condition Survey | IRC:SP:19 | - | - | - | -
| Inventory & Condition Survey for Existing Bridges, Culverts & Structures | IRC:SP:35 | - | - | - | -
| Inventory for Existing Pavement composition | - | - | - | - | -
| Traffic surveys & Analysis (TVC/ATCC, OD survey, Axle load, Turning movement, Speed-Delay etc..) | - | - | - | - | -
| Collection of Accident data (FIR) from the Police Station | - | - | - | - | -
| Collection & Testing of Various materials (e.g. Cement, Steel, Aggregates, Bitumen) & Borrow area soil | - | - | - | - | -
| Collection of Soil Sample by Digging test Pits adjacent to road along the Existing road | - | - | - | - | -
-- | Detailed Topographic Survey & Alignment Design
| Taking Longitudinal and Cross sections of existing road and Collection of Existing Utilities details and Road side affeccted structures etc. | - | - | - | - | -
| Geometric Design of proposed Alignment (Horizontal & Verticle) | - | - | - | - | -
► | Report Preparation
► | Main Report
-- | Executive summary & Introduction | - | Volume-1 | - | - | -
-- | Socio Economic Profile | - | Volume-1 | - | - | -
-- | Existing alignment & Proposed provision of Roads & Structures | - | Volume-1 | - | - | -
-- | Summary of Traffic survey & Analysis | - | Volume-1 | - | - | -
-- | Summary of Site Investigation | - | Volume-1 | - | - | -
-- | Environmental Impact Assesement | - | Volume-1 | - | - | -
-- | Social Impact Assesement | - | Volume-1 | - | - | -
-- | Cost Estimates (Tentative/Preliminary) (Based on Preliminary Rate analysis)
| Cost estimate of Main Road, Service road, Protection walls, Toll Plaza, Traffic signs & Safety measures, Bridges, Culvert & Structures | - | Volume-1 | - | - | -
-- | Viability and Financing Options
| Economic Analysis | IRC SP:30-2009 | Volume-1 | - | - | -
| Financial Analysis (On base of The Gazette of India : Extraordinary (Regd. No. 33004/99)) | - | Volume-1 | - | - | -
► | Annexures
-- | Existing details along the road
| Details of Existing Utilities services | - | Volume-2 | Annexure-1 | - | -
| Details of Existing Road side affeccted structures | - |  | Annexure-2 | - | -
| Details of Existing Religious structures | - |  | Annexure-3 | - | -
-- | Traffic survey & Analysis
| Classified Traffic Volume count survey | IRC SP:19 | Volume-2 | Annexure-4 | - | -
| Axle Load Survey | IRC SP:19 |  | Annexure-5 | - | -
| Origin & Destination survey | IRC: 102 |  | Annexure-6 | - | -
| Intersection Volume Count (Turning movement survey) | IRC SP:41 |  | Annexure-7 | - | -
| Speed-Delay Survey | IRC: 102 |  | Annexure-8 | - | -
| Pedestrian / Animal Cross traffic Count | - |  | Annexure-9 | - | -
| Truck Terminal survey | - |  | Annexure-10 | - | -
-- | Accident Analysis
| Analysis of Accident data | - | Volume-2 | Annexure-11 | - | -
-- | Pavement Condition survey
| Existing Pavement Composition & Existing Pavement Condition | - | Volume-2 | Annexure-12 | - | -
-- | Pavement Investigation
| Pavement Roughness (BI/NSV) | IRC SP:16 | Volume-2 | Annexure-13 | - | -
| Pavement Structural Strenth (BBD / FWD) | IRC:81 / IRC:115 & 117 |  | Annexure-14 | - | -
-- | Pavement Design
| Initial Composition of Pavement for CC & BT roads | IRC:37 & 58 | Volume-2 | Annexure-15 | - | -
-- | Subgrade Characteristics and Strength
| Result of In-situ density, moisture content and Field CBR of Each test Pits | IS:2720 | Volume-2 | Annexure-16 | - | -
| Result of Grain size and Atterberg Limits of Each test Pits | IS:2720 |  |  | - | -
| Result of Laboratory density, moisture content and CBR of Each test Pits | IS:2720 |  |  | - | -
-- | Inventory & Condition Survey for Bridges, CD works & Structures
| Summary of Inventory & Condition survey for CD works | - | Volume-2 | Annexure-18 | - | -
| Summary of Inventory & Condition survey for Bridges | - |  | Annexure-19 | - | -
| Summary of Inventory & Condition survey for Structures | - |  | Annexure-20 | - | -
-- | Preliminary land acquisition
| Details of Preliminary land acquisition (Area & Cost of Land to be acquired) | - | Volume-2 | Annexure-21 | - | -
► | Alignment Drawing
| Preparation & Submission of Proposed alignment layout showing Existing & Proposed ROW, (Including Location of Bus bay with shelter, Truck lay bay & Toll plaza) | - | Volume-3 | - | - | -
► | Submission & Approval
| Submission of Draft Feasibility Report | - | - | - | - | -
| Comments from Concern approval authority & Its Compliance, if any | - | - | - | - | -
| Approval of Draft Feasibility Report | - | - | - | - | -
3 | Final Alignment Report / Final Feasibility Report |  |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Approval of Alignment from Concern Authority
| Presentations infront of Concern Approval Authority for Alignment Approval | - | - | - | - | -
| Approval of Proposed Alignment | - | - | - | - | -
► | Submission & Approval
| Prepration & Submission of Final Feasibility Report | - | - | - | - | -
| RA Bill (On Submission of Final Feasibility Report) | - | - | - | - | -
| Approval of Final Feasibility Report | - | - | - | - | -
| Preparation & Submission of Final Alignment Report | - | - | - | - | -
| RA Bill (On Submission of Final Alignment Report) | - | - | - | - | -
| Approval of Final Alignment Report | - | - | - | - | -
4 | Detailed Project Report (DPR) |  |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Reconnaissance Survey & Miscellaneous Activities
| Topography Survey / Dron survey on Proposed Bypass & Realignment / Proposed approved Alignment | - | - | - | - | -
| Shifting & Finalization of Horizontal alignment for Minimize major demolistion of existing structure, if any | - | - | - | - | -
| Preparation & Verification on site for Final list of Demolisition of Existing Structures on new alignment | - | - | - | - | -
| Preparation of Final Pavement design report | - | - | - | - | -
| Finalisation of Lane Configuration and Preparation of Final TCS | - | - | - | - | -
| Prepare Final list of proposed strutures (incl. Nos. & Length of Bore reqd. Its Coordinate & RL for geo technical investigation ) | - | - | - | - | -
| Preparation layout drawing for new alignment showing Existing & Proposed ROW, (Including Proposed structures, Location of Bus bay with shelter, Truck lay bay, Toll plaza, Overtaking zone, Junction improvement) | - | - | - | - | -
| Profile Design on Proposed new alignement | - | - | - | - | -
| Hydraulic & Hydrological Investigation for proposed structures | - | - | - | - | -
| Workout Final FRL, Span and Type of Proposed Bridges & Structures | - | - | - | - | -
| Final Profile Design of Proposed new alignement (If FRL revised due to Design Discharge) | - | - | - | - | -
| Geo Technical Investigation and sub soil Exploration at proposed structures | - | - | - | - | -
| Verification of Bore details On site / Office | - | - | - | - | -
| Work out Size of footing (MNB/MJB/ROB etc) & Design SBC of proposed structures | - | - | - | - | -
| Report on Geo Technical Investigation and sub soil Exploration | - | - | - | - | -
| Preparation of GAD of Proposed structures | - | - | - | - | -
| Preparation or Submission of EIRR report | - | - | - | - | -
| Preparation or Submission of FIRR report | - | - | - | - | -
► | Main Report
| Submission of Main Report | - | Volume - 1 | - | - | -
► | Detail Design of Road, Pavements, Bridges and Structures.
| Design of Embankment | - | Volume - 2 | - | - | -
| Design of Bridges and Structures |  |  |  | - | -
| Design of Drainage system |  |  |  | - | -
| Traffic Safety Features, Road Furniture and Road Markings |  |  |  | - | -
| Arboriculture and Landscaping |  |  |  | - | -
| Toll Plaza |  |  |  | - | -
| Weighing Station, Parking Areas and Rest Areas |  |  |  | - | -
| Office-cum-Residential Complex for PIU |  |  |  | - | -
| Submission of Design Report |  |  |  | - | -
► | Material Report
| Submission of Material Report | - | Volume - 3 | - | - | -
► | Environmental & Social Impact Assessment
| Environmental Assessment Report including Environmental management Plan (EMP) | - | Volume - 4 | - | - | -
| Resettlement Action Plan (RAP) |  |  |  | - | -
| Social Assessment |  |  |  | - | -
► | Technical Specifications
| Submission of Item wise Techincal Specification | - | Volume - 5 | - | - | -
► | Estimation of Quantities and Project Costs
| Rate Analysis | - |  | - | - | -
| Cost Estimates | - |  | - | - | -
| Bills of Quantities (BOQ) | - |  | - | - | -
► | Drawings
| Submission seprate volume of drawings | - | Volume - 6 | - | - | -
► | Submission & Approval DPR
| Submission of Draft DPR | - | - | - | - | -
| RA Bill (On Submission of Draft DPR) | - | - | - | - | -
| Approval of Draft DPR | - | - | - | - | -
| Preparation of Final DPR | - | - | - | - | -
| Submission of Final DPR | - | - | - | - | -
| RA Bill (On Submission of Final DPR) | - | - | - | - | -
| Approval of Final DPR | - | - | - | - | -
5 | Draft / Final LA & Clearance I Report |  |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | Data Collections
Collection of Maps & Collection of Land revenue records etc.
Collection of Reserved Forest Survey nos. and Protected Forest Chainage from concern DCF office
► | Submission & Approval
| Preparation & Submission of LA & Clearance I Report |  | Volume - 1
| Preparation & Submission of Strip Plan / LA Plan |  | Volume - 2
| Preparation & Submission of Utility relocation plan | IRC:98
Approval of LA & Clearance I Report
► | Clearnace Proposal
Preparation & Submission of of Clearance proposals for which we seeks approvals (e.g. Utilities, Forest, WL, EFZ, ESZ, CRZ, ENV, Railway, irrigation & Other Dept. etc....)
RA Bill (On Submission of Clearance proposal)
6 | Draft / Final Technical Schedule |  |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | Civil Work Contract Agreement
Preparation & Submission of EPC Agreement / BOT Agreement / HAM Agreement
Preparation & Submission of Technical Schedule
Aprroval of EPC Document incl. Technical Schedule
RA Bill (On Aprroval of EPC Document incl. Technical Schedule)
7 | Draft / Final LA & Clearance II, III & IV Report |  |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Land Acquisition
Lisening for Appointment of CALA
Publication of 3(a) Notification in Gazette
Joint Site Visit (PIA (MoRT&H)-Public Implementing Agency / PD (NHAI)-Project Director With DPR Consultant & Client) incl. Photograph of Existing structures condition on Proposed Alignment
Publication of 3(A) Notification in Gazette
3(B) Notification - Power to enter for survey
Fixing of Boundary pillar for PROW marking & Centre line marking
Joint measurement survey with DILR officials
Appointment of Govt. valuer for Valuation of existing residential structure /Well etc need to be demolish
3.C Land Holders Represent therir case infront of CALA within 21 Days of Publication of 3a & 3A in Gazatte
Report given by CALA to Central Govt. (Through Proper channel) for issuance of 3D
Publication of 3D Notification
RA Bill (On Publication of 3D Notification)
| 3(G) Notification -Determination of Amount payable as compensation and Call Land Holder for Account no. & Land Holdindg authentication |  | LA III Report
3(H)- Central Govt. deposite Compensation amount to CALA
| 3(E)- Power to take possesion Within 60Days of Issuance of 3(E) Land owner deliver possession of land to CALA |  | LA IV Report
► | Submission & Approval
Preparation & submission of Draft LA Report
Submission of Estimated Cost of Land Acquisition
Approval of Draft LA Report
Approval of Estimated costs of Land acquisition
Preparation & Submission of Final LA report incl. Gazette Notification of 3a, 3A & 3D
Preparation & Submission of Final Estimated costs of land acquisition
RA Bill (On Submission of Final LA Report)
► | Forest / Wild life Clearance / CRZ / ESZ / EFZ
Online applications
Submission of Forest Proposal to Concern DCF office
Forest / Wild life Clearance Stage-I Approval (Principal Approval from RO(HQ) New Delhi)
RA Bill (On Forest / Wild life Principal Approval))
Forest / Wild life Clearance Stage-II Approval (Final Approval from MoEFCC Head office, New Delhi)
RA Bill (On Forest / Wild life Stage-II/Final Approval))
► | FRA Certificate
Submission of proposal for FRA clearance
► | GAD Approval (From Railway)
Final approval of GAD from CBE Mumbai
► | Irrigation Department, Electricity Department. and any other concerned agencies
Final approval of project related clearance.
► | Submission
| Submission of Clearacne Report (Environment, Forest Department, Wild life, CRZ, Railways in respect of ROB/ RUBs, Irrigation Department, Electricity Department. and any other concerned agencies) with final approval for project related clearance. |  | LA IV Report
Retention to be released after 3 years

## Sheet1 (hidden)
Checklist (DPR Projects)
Project Management
Award of Project (Receiving LOA)
Submission of Performance security / BG
Letter for work execution (Receiving Work order)
Establish Team for Preparing DPR & Invites other Dept. heads for meeting & Discussions
Fix Rolls & Responsibility and prepare schedule of execution
Action plan to accelerate activities which was delay from schedule & Relieving measures to kept project on track
Monthly Progress report
Reconnaissance Survey
Exisitng Road Inventory survey as per IRC:SP:19
Exisitng Chainage wise Pavement condition/Composition survey as per IRC:SP:19
Inventory & Condition Survey for Exisitng CD Structure, Bridges, Structures as per IRC:SP:35
Public Consulation including consultation with Communities located along the road, NGOs working in the area & other stake-holders
Socio Economic impact Study
Videography of entire highway stretch
Walkthrough on proposed new greenfield alignment/Bypass/Realignment
Collection from field / Data Preparation
Collection of Soil Sample by Digging test Pits along road alignment (For In-situ physical properties, Laboratory physical properties, Chemical Properties etc)
Collection of Various materials (e.g. Cement, Steel, Aggregates, Bitumen, Emulsion, Borrow area soil, Water sample etc)
Collection of Accident data (FIR) from the Police Station
Collection of Maps & Collection of Land revenue records etc.
Collection of Reserved Forest Survey nos. and Protected Forest Chainage from concern DCF office / collect government notifications declaring forest land as PF/RF and its maps.
Collection of utility shifting estimates/Quotations from all user agencies
DPR Data Sheets Preparaion (For Final Approved Alignment)
Lane Configurations Sheet
Structure list
Existing & Proposed Final ROW List
Bus Bay & Truck Lay Bye List
Village Boundary List
Terrain & Builtup areas list
Junction List with improvement details
Technical Note
Surveys at Site
Traffic survey & Analysis
Classified Traffic Volume count survey
Axle Load Survey
Origin & Destination survey (Passengers & Goods trips)
Intersection Volume Count (Turning movement survey)
Speed-Delay Survey
Analysis on Pedestrian / Animal flow characteristics
Truck Terminal survey
Existing Pavement Structural Strenth (BBD / FWD) IRC:81
Existing Pavement Roughness Tests IRC:SP:16
Detailed Topographic Survey (Existing alignment) Using LiDAR or better technology
Ground Penetrating Radar (GPR) Survey for detection of sub-surface utilities
Geo-technical and sub soil Exploration at Existing/proposed structures as per IRC:78
Detailed Topography Survey / Dron survey on approved Bypass/Realignment /Proposed approved Alignment
Joint Measurement survey with utilities user agencies
Fixing of Boundary pillar for PROW marking & Centre line marking
Joint Measurement survey with DILR officials for forest clearance
Joint Measurement survey with Govt. Valuer for valuation of demolish structures
Joint Site Visit with Concern Forest officials of Reserved forest for Punchnama of the proposed diversion & marking kharda of trees to be cut.
Joint Site Visit with Concern Forest officials of Protected forest for Punchnama of the proposed diversion & marking kharda of trees to be cut.
Detailed Design
Draft Geometric Design of a proposed alignment (Plan & Profile Drawings)
Hydraulic & Hydrological Investigation for proposed structures as per IRC:SP:13 & IRC:5
Final Geometric Design of a proposed alignment (Plan & Profile Drawings)
Intersections, Grade separators & Interchanges with ramps
Typical Cross section Design & Drawings
Road Safety Furniture Drawings incl. Road Signs, Pavement marking, Safety barrier, Railings, Delineators, Chevron markings, Traffic attenuators, Crash barriers, overhead signs etc
Preparation of GAD of Proposed structures
Roadside Drain Design & Drawings (RCC / Earthen)
Protection work Design & Drawings (Toe wall /Retaining Wall / Brest wall / RE wall etc..)
Arboriculture and Landscaping Design & Drawings
Toll Plaza Design Design & Drawings(Incl.Weighing Station, Parking Areas etc.)
Rest Area Design & Drawings
Bus Bay, Truck Lay Bye Pedestrian crossing etc design & Drawings
Report Preparation & Submissions
Draft / Final Inception Report & QAP
Draft / Final Feasibility Report
Traffic Surveys Analysis & Report
Accident Analysis Report (Identification of black spots on project stretch)
Environmental Impact Assesement Study (Land, Air, Water resources, Noise & Biological envirnmental details / impact / mitigation measures ) including Environmental management Plan
Socio Economic impact Study including Resettlement Action Plan (RAP)
Alignment Options study with merits & demerits
Cost Estimate with Rate Analysis
Normative Cost
Life cycle cost analysis
Economical Internal Rate of Return (EIRR) report as per IRC:SP:30
Financial Internal Rate of Return (FIRR) report
Draft / Final Detailed Project Report (DPR)
Material Report
Pavement Design Report
Design Base Report - Structures / Final road Alignment / Drain
Hydraulic Design report - Structures / Road Side Drain (Earthen & RCC )
Geotechnical Investigation Report
Environmental Assesement Report
Detailed Bills of Quantities (BOQ) with rate analysis
Draft / Final LA & Clearance I Report
Land acquisition report (incl.LA/Strip Plan, 3(a) & 3(A) Notifications/Publications)
Utilities shifting proposals to all user agencies
Utility relocation plan incl. Details of properties / Utilities
Draft / Final LA & Clearance II Report
Estimated cost of land acquisition
Land acquisition report (incl. 3(D) Notifications/Publications)
Clearacne Report (Environment, Forest Department, Wild life, CRZ, Railways in respect of ROB/ RUBs, Irrigation Department, Electricity Department. and any other concerned agencies) with final approval for project related clearance
Valuations of structures need to be demolish
Land Award report (Completion of award declaration (3G) for 90% of land parcels identified in LA II report)
Land Possession report Receipt of land possession certificates (3E) for 90% of all land parcels identified in LA II report)
Bid documents and civil works contract agreement along with technical schedules
Approval from Authority
Draft Inception Report & QAP
Final Inception Report & QAP
Draft Feasibility Report
Alignment Options Report
Alignment Approval by authority
Final Feasibility Report
Final Alignment Report
Draft Detailed Project Report (DPR)
Final Detailed Project Report (DPR)
Draft LA & Clearance I Report
Final LA & Clearance I Report
Utility shifting estimates
Draft LA & Clearance II Report
Final LA & Clearance II Report
Bid documents and civil works contract agreement along with technical schedules
Clearances
FRA Certificate
Submission of PF/RF proposal to collector
Submission of PF/RF proposal from collector to SDM
Submission of PF/RF proposal from SDM to Prayojna Vahivatdar office
Approval of of PF/RF proposal & Recommendation for issue FRA Certificate from Prayojna Vahivatdar office to SDM
Approval of of PF/RF proposal & Recommendation for issue FRA Certificate from SDM to Collector
Issue FRA Certificate of PF/RF by Collector
Forest Clearances
Submission of Online proposal by user agency to Concern DCF, Division office (Form-A, Part-1)
Submission of Proposal in Physical file by user agency to Concern DCF, Division office
Submission of field visit report with Punchnama & Marking Kharda by RFO in DCF, Division office
Submission of Online proposal & Physical files by DCF to concern CCF,circle office (Form-A, Part-2)
Submission of Online proposal & Physical files by CCF to Nodal office (APCCF) (Form-A, Part-3)
Submission of Physical files to PCCF(HoFF)
Submission of Online proposal & Physical files by Nodal office (APCCF) to Secretary-(F&ED) (Form-A, Part-4)
Submission of Physical files to Hon’ble. MoS and Hon’ble Cabinet Minister
Online submission of Proposals and submission of physical file to APCCF-Regional Office, Western Zone-Bhopal
Online submission of Proposals and submission of physical file to RO (HQ) new Delhi
Principle Approval by APCCF-Regional Office, Western Zone-Bhopal (<40 Ha.) / RO (HQ) new Delhi
Demand Note for payment of NPV and compliance report
Apply for obtaining the Demand Note for NPV.
Processing for Payment of NPV by User Agency.
To apply to get Demand Note for C.A. Scheme for double degraded forest area or to hand over land bank to Forest Department and to get C.A. Scheme to pay to Forest Department.
To prepare compliance report and submit to concern DCF.
Persual for obtaining Working Permission
Submission of Compliance Report to CCF.
Submission of compliance report to Nodal Officer.
Submission of compliance report to PCCF.
Submission of compliance report to Secretary-F&ED.
Submission of compliance report to Regional Office/MoEF
Perusal for final Permission at Regional Office (Stage-II Approval & Memorandum)
Pursue Regional Office/MoEF for getting final approval.
Application to Obtain Government Notification. (Memorandum)
Application for Removal of Trees at Division Level
Other Clearances, if any
Final approval of GAD of ROB from CBE Mumbai
NOC from concern Irrigation department
NOC from concern NHAI/R&B/NHIDCL/PWD etc.
NOC from concern Wild life department
NOC from concern Archeology department
Approval of Environment Clearance (EC)

## DPR Stage(NEW)...9.2.24
DETAILED PROJECT REPORT (DPR) STAGE WISE ACTIVITY SCHEDULE
Sr No. | Activity Description | Reference | Volume | Annexure | Remark
0 | Project Management
| Award of Project / LOA | - | - | - | -
| Submission of Performance security / Bank Guarantee/ FDR | - | - | - | -
Collect hard copy of Submitted Performance security / Bank Guarantee/ FDR
Renewal of Expired Performance security / Bank Guarantee/ FDR and Collect Hard Copy
Signing the Tender Agreement
Collect Hard copy of Signed Agreement
Collect Team Compositon of of awarded Tender
Collect Filled Schedule-B of awarded Tender
Letter for Proceeding / Work order
Collect hard copy of Insurance Policy (As per tender requirement) i.e PL, PI & WC Policy etc.
Renewal of Expired Insurance Policy and Collect Hard Copy
After Attending Meetings with authority or any respective other authority regarding Project. Prepare Minutes of Meeting and issued officially.
| Maintain Inward and Outward Letters | - | - | - | -
| Preparation and Submission of Extension of Time Limit Proposal | - | - | - | -
| Preparation and Submission of Excess / Extra Proposal, if any | - | - | - | -
1 | Draft / Final Inception Report & QAP |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | Reconnaissance Survey
| Kick-off Meeting with client & preliminary Project site visit | -
| Geometric Design of Existing Alignment | -
| Existing Road Inventory | IRC:SP:19 | - | - | -
| Existing Bridges, Culverts & Structures Inventory | IRC:SP:35
► | Subnission & Approval
| Prepration & Submission of Draft Inception Report & QAP | - | - | - | -
| Comments from Concern approval authority & Its Compliance, if any on Draft Inception Report & QAP | - | - | - | -
| Prepration & Submission of Final Inception Report & QAP | - | - | - | -
| Approval of Final Inception Report & QAP | - | - | - | -
| RA Bill (On submission of Final Inception Report & QAP) | - | - | - | -
2 | Draft / Final Feasibility Report (Incl. Alignment Option / Final Alignment report) |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Data Preparations / Collections (Alignment report)
| Videography of entire Existing highway stretch | - | - | - | -
| Collection of Accident data (FIR) from the Police Station | - | - | - | -
| Collection of Petrol pump selling Data | - | - | - | For AADT Calculation
► | Reconnaissance Survey (Alignment report)
| Traffic surveys & Analysis | - |  | - | -
| Classified Traffic Volume count survey | IRC SP:19 | - | Appendix-1 | Traffic Report
| Axle Load Survey | IRC SP:19
| Origin & Destination survey | IRC: 102
| Intersection Volume Count (Turning movement survey) | IRC SP:41
| Speed-Delay Survey | IRC: 102
| Pedestrian / Animal Cross traffic Count | -
| Truck Terminal survey | -
| Identification of Black Spots | - |  | Appendix-6 | Black spot report
| Geometric Design for various Alignment options | - | - | - | -
| Walkthrough on proposed new greenfield alignment/Bypass/Realignment/Existing alignment | - | - | - | Check for Alignment feasibilty as well as terrain and underground major utility existance / Hurdles
| Public Consulation including consultation with Communities, NGOs working in the area & other stake-holders | - | - | - | -
| Preparation of Alignment Option Report & Presentation |  | Volume - 1
► | Reconnaissance Survey & Data Preparations / Collections (For Feasibility report after alignment approval)
Detailed Topographic Survey
| Preparation of Feasibility Report | - | Volume - 2 | - | Refer Appendix VIII in Std.DPR RFP-Feb-24
| Collection & Testing of Various materials (e.g. Cement, Steel, Aggregates, Bitumen, water, Fly Ash, Borrow area soil, Embakment Soil & Other locally availabe material (eg. Hume pipes etc..) (Physical & Chemical Properties) | IRC:SP:19 | - | Appendix-10 | Material Report Same Shall be submit in DPR (Vol.3)
| Existing Pavement Condition, Composition Survey & Roughness survey (BI/NSV) | IRC:SP:19 & IRC SP:16 | - | Appendix-2 | Add Road Inventory in report (NSV Report)
| Condition survey for Existing CD works, Bridges & Structures | IRC:SP:35 | - | Appendix-7 | Inv. & Condition survey report Add CD work, bridge & Str. Inventory in report
| Subgrade Characteristics and Strength survey - Collection of Existing Sub-Grade Soil Sample by Digging test Pits & Testing physical & Chemical Properties |  | - | Appendix-3 | FWD Report
| Pavement Structural Strenth Survey (BBD / FWD) | IRC:81 / IRC:115 & 117
| Geo Technical Investigation and sub soil Exploration at proposed CD work, Bridges & structures | IRC:78 | - | Appendix-8 | Geo-technical report
| Hydraulic and Hydrological Survey | IRC:SP:13 and IRC:5 | - | Appendix-9 | Hydraulic Report
| Preliminary environmental assessment | IRC:SP:19 | - | Appendix-11 | Environment and Social Impact Assessment report Same Shall be submit in DPR (Vol.4)
| Socio Economic impact Study (Initial social assessment/ preliminary LA resettlement plan) | IRC:SP:19
| Pavement Design report (With Alternative Design Options) |  | - | Appendix-4
| Rate Analysis | - | - | Appendix-12 | Same Shall be submit in DPR (Vol.6,7 & 8)
| Cost Estimate |  |  | Appendix-13
Bill of Quantities
| Economic analysis | IRC SP:30-2009 | - | Appendix-5 | Economic and financial analysis report
| Financial Analysis (On base of The Gazette of India : Extraordinary (Regd. No. 33004/99)) | Gazette Notifications
| Preliminary land acquisition Details of Existing and Proposed ROW Details about ownership of land to beacquired Details about Area of Acquistion and Tentative Cost of Land Acquisition Details of Existing Road side affeccted structures & Cost of Demolision |  | - | Appendix-14
| Strip plan and Alignment Drawing |  | - | Appendix-15 | Only Alignment Plan & TCS
► | Submission & Approval
| Submission of Alignment Option Report | - | - | - | -
| Alignment approval from Concern approval authority | - | - | - | -
| Submission of Final Alignment Report | - | - | - | -
| Approval of Final Alignment Report | - | - | - | -
| RA Bill (On Approval of Final Alignment Report) | - | - | - | -
| Submission of Draft Feasibility Report | - | - | - | -
| Comments from Concern approval authority & Its Compliance, if any on Draft Feasibility Report | - | - | - | -
| Submission of Final Feasibility Report | - | - | - | -
| RA Bill (On submission of Final Feasibility Report) | - | - | - | -
3 | LA & Clearance I Report |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | LA-I Report
Collection of Village Maps & Collection of Land revenue records etc.
Shifting & Finalization of Horizontal alignment for Minimize major demolistion of existing structure.
| Liasion for appointment of CALA & Publication of 3a Gazette Notification |  |  | Appendix-I: Publications | Atteched Published 3a
| Preparation of Draft 3A Notifications |  |  |  | Atteched Published / Draft 3A
| Submission of Estimated Cost of Land Acquisition |  |  | Appendix-II
| Submission of LA-I Report incl. Strip / LA Plan | Incl. Ex.ROW & PROW, CL, existing BT and proposed BT edge Details of centreline, existing structures,C.wall, Tube well etc. road furniture and other features
Comments from Concern approval authority & Its Compliance, if any LA-I Report
Submission of Final LA-I Report incl. Strip/LA Plan
RA Bill (On Submission of Final LA-I Report incl. Strip/LA Plant)
► | Utility-I Report
Identification of surface utilities
Ground Penetrating Radar (GPR) Survey for identification of sub-surface utilities
Submission of intimation / identification letter from authority to Utility owner
Consultation with Utility agency & Discussion on Tentative Cost of relocation
Submission of Utility Shifting proposals to user agency
| Submission of Utility-I Report & Utility relocation plan / Utility plan |  |  |  | Km wise Utility details attached in Utility plan
RA Bill (On Submission of Utility Proposals and Utility Shifting Plan)
► | Clearance-I Report
Environment Clearance
Initial consultation with competent authority
Submission of of Clearance proposals
Forest Clearance
Initial consultation with competent authority
Collection of Reserved Forest Survey nos. and Protected Forest Chainage from concern DCF office
Details/cost of trees being felled basis concerned District Forest Office
Submission of of Clearance proposals
Wildlife Clearance
Initial consultation with competent authority
Details/cost of trees being felled basis concerned District Forest Office
Submission of of Clearance proposals
CRZ Clearance
Initial consultation with competent authority
Preparation of EIA Report
Mapping of CRZ Boundary on Map (i.e. LOW tide, Hide Tide line & CRZ Area ) by Autorised Agency
Preparation and submission of documents along with Form-I
Other Clearance
Initial consultation with competent authority (i.e. Railway, Irrigation,Archeology etc….)
Submission of of Clearance proposals (GAD Submission for approval)
Submission of Clearance-I Report
RA Bill (On Submission of Clearance-I Report )
4 | Detailed Project Report (DPR) |  |  |  | (Approved By: AS/ADG/CE-cordinator, MoRT&H)
► | Reconnaissance Survey & Miscellaneous Activities
| Topography Survey on Proposed Bypass & Realignment / Proposed approved Alignment | - | - | - | If pending in FS study
| Prepare Final list of proposed strutures (Chainage, Span etc..) (for CD works, Bridges & Structures) | - | - | - | -
| Final Geometric Design of approved alignment (Plan & Profile) (As per Final FRL of proposed by design department for CD works, Bridges & Structures) | - | - | - | -
| Finalise Lane Configuration and Preparation of Final TCS | - | - | - | -
► | Main Report
| Submission of Main Report | - | Volume - 1 | - | Refer Appendix VIII in Std.DPR RFP-Feb-24
► | Design Based Report (DBR) |  |  |  | -
| Design of road Design based report for Design of alignment, Embankment, Highway Lighting, Arboriculture and Landscaping, Toll Plaza, Weighing Station, Parking Areas, Rest Areas, Office-cum-Residential Complex etc. | - | Volume - 2 (Part-1) | - | -
| Traffic Report (incl. Volume count, Axel load, TMC, O-D survey etc..) | - | - | Appendix-1
| NSV Report (incl. Road Inventory, Pavement Condition, Composition and Roughness) | - | - | Appendix-2
| FWD Report (inc. Existing sub-grade soil test report) | - | - | Appendix-3
| Pavement Design report | - | - | Appendix-4 | Final Design From alternative Option given in F.S. Report
| Economic and financial analysis report | - | - | Appendix-5
| Black Spot Audit report | - | - | Appendix-6
| Design of Structures Design based report for Proposed Bridges, Protection works, CD Works & Structures etc. | - | Volume - 2 (Part-2) | -
| Inventory & Condition survey report (Existing CD works, Bridges & Structures) | - | - | Appendix-7
| Geo-technical and sub-soil explorations report | - | - | Appendix-8
| Hydraulic & Hydrological Investigation report | - | - | Appendix-9
► | Material Report
| Collection & Testing of Various materials (e.g. Cement, Steel, Aggregates, Bitumen, water, Fly Ash, Borrow area soil, Embakment Soil & Other locally availabe material (eg. Hume pipes etc..) (Physical & Chemical Properties) |  | Volume - 3 |  | Appendix-10 in Feasibility report
► | Environment and Social Impact Assessment report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP):
| Environmental Assessment Report including Environmental management Plan (EMP) |  | Volume - 4 |  | Appendix-11 in Feasibility report
Socio Economic impact Study (Initial social assessment/ preliminary LA resettlement plan) Resettlement Action Plan (RAP)
► | Technical Specifications
| Submission of Techincal Specification (Special technical specifications which are not covered by MOST Specifications) | - | Volume - 5 | -
► | Estimation of Quantities and Project Costs
| Rate Analysis | - | Volume - 6 | - | Appendix-12 in FS report
| Detailed Estimates & | - | Volume - 7 | - | Appendix-13 in Feasibility report
| Bills of Quantities (BOQ) | - | Volume - 8 | -
► | Drawings
| Drawing includes Road : Curve Table, Typical cross sections, Lane configuration/TCS Schedule, Plan-Profile, Road furniture plan, Junction improvement etc Structure : GADs, Protection work (Retaining wall, Toe wall, CB etc.) and Project Facility : Toll Plazas, Rest Area, Bus bays, Truck lay buys etc.... | - | Volume - 9 | -
► | Drainage Plan
| Drainage Design Report | - | Volume - 10 (Part-1) | - | -
| Drainage plan prepared on basis of contours of the area, outlet availability and discharge requirements including discharge at the outfall from drains of local bodies Drawing includes (Drainage plan & Cross-sections of RCC Drain etc) | - | Volume - 10 (Part-2) | - | -
► | Submission & Approval DPR
| Submission of Draft DPR | - | - | - | -
| Comments from Concern approval authority & Its Compliance, if any on Draft DPR | - | - | - | -
| Submission of Final DPR | - | - | - | -
| Approval of Final DPR | - | - | - | -
RA Bill (On approval of Final DPR, Documents & Drawings )
5 | Draft / Final Technical Schedule |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | Civil Work Contract Agreement
Submission of Draft Civil work contract Agreement (EPC / BOT / HAM / Anyother) along with technical schedule
Submission of Bid Documents (RFP / NIT etc..)
Approval of Bid Documents (RFP / NIT etc..)
RA Bill (On Approval of Bid Documents & Civil work Contract Agreement incl. Technical Schedule)
Packgae Award to Concessionaire/Contractor
RA Bill (On Earlier of Packgae Award to Concessionaire/Contractor or 6 months from launch of tender process )
6 | LA & Clearance II Report |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
► | LA-II Report
Liasion for Publication of 3A Gazette Notification
Fixing of Boundary pillar for PROW marking & Centre line marking
Joint measurement survey with DILR officials / competent authority
Valuation of existing properties atteched with the acquistion land
Liasion for Publication of 3D Gazette Notification
Submission of LA-II Report incl. Final Strip/LA Plan
RA Bill (On 3D Publication & Submission of LA-II Report )
► | Utility-II Report
Joint site inspection with competent authority
Submission of Utility Shifting Estimates / Quotation
Collection of NO upgradation certificate
Approval of Utility Shifting Estimates / Quotation
Submission of Utility-II Report & Final Utility relocation plan
RA Bill (On approval of Utility shifting estimates & Submission of Utility-II Report)
► | Clearance-II Report
Environment Clearance
Liasion for Public Hearing
Final environment clearance by competent authority
Forest Clearance
Joint site inspection with DFO / competent authority
Liasion for FRA certificate
Stage I forest clearance approval by competent authority (Principal Approval)
Stage II forest clearance approval by competent authority (Final Approval)
Wildlife Clearance
Joint site inspection with DFO / competent authority
Stage I Wild clearance approval by competent authority (Principal Approval)
Stage II Wild clearance approval by competent authority (Final Approval)
CRZ Clearance
Site Visit, to be carried out by GCZMA/State Govt. for site verification
Presentation (infront of committee members)
Final CRZ clearance by competent authority
Other Clearance
Final GAD Approval from concern approval autority (i.e. Railway, Irrigation etc..)
Submission of Final Clearance-II Report
RA Bill (On Submission of Final Clearance-II Report )
7 | Land Award Report (LA-III Report) |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
Liasion for Award Decleration (3G)
| Submission of Land Award Report |  |  |  | Min. 90% of 3D
RA Bill (On Submission of Land Award Report )
8 | Land possession Report (LA-IV Report) |  |  |  | (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
Liasion for Deposition of compensation amount by Govt. to CALA 3(H)
Liasion for Amount Disbursement to Land owners by CALA
Receipt of Land Possession Certificate 3(E)
| Submission of Land possession Report |  |  |  | Min. 90% of 3D
RA Bill (On Submission of Land possession Report )
Retention amount release Aftrer 3 year from work start & Project COD whichever is earlier

## DPR Activity Checklist
|  | ACTIVITY CHECKLIST FOR DPR WORK | [7 empty] | ACTIVITY CHECKLIST FOR DPR WORK
| PROJECTS : | SOU HSC | Ank HSC | Sachin | Navsari | Amod | NH848 | Rajpipla | Palanpur | Porbandar | Assam | Nagaland | CBE
0 | Project Management
0.1 | Award of Project / LOA
0.2 | Submission of Performance security / Bank Guarantee/ FDR
0.3 | Collect hard copy of Submitted Performance security / Bank Guarantee/ FDR
0.4 | Renewal of Expired Performance security / Bank Guarantee/ FDR and Collect Hard Copy
0.5 | Signing the Tender Agreement
0.6 | Collect Hard copy of Signed Agreement
0.7 | Collect Team Compositon of of awarded Tender
0.8 | Collect Filled Schedule-B of awarded Tender
0.9 | Letter for Proceeding / Work order
0.10 | Collect hard copy of Insurance Policy (As per tender requirement) i.e PL, PI & WC Policy etc.
0.11 | Renewal of Expired Insurance Policy and Collect Hard Copy
0.12 | After Attending Meetings with authority or any respective other authority regarding Project. Prepare Minutes of Meeting and issued officially.
0.13 | Maintain Inward and Outward Letters
0.14 | Preparation and Submission of Extension of Time Limit Proposal
0.15 | Preparation and Submission of Excess / Extra Proposal, if any
0.16
0.17
0.18
0.19
1 | Inception report & QAP
1.1 | Kick-off Meeting with client & preliminary Project site visit
1.2 | Geometric Design of a Existing alignment
1.3 | Submission of QAP
1.4 | Exisitng Road & Existing Bridges, Culverts & Structures Inventory
1.5 | Submission of Draft Inception Report
1.6 | Presentation on Inception report
1.7 | Comments of Client on Draft Inception Report & QAP
1.8 | Submission of Final Inception Report & QAP
1.9 | Approval of Final Inception Report & QAP
2 | Feasibility Report incl. Alignment Option Report
2.1 | Conducting Traffic surveys
Classified Traffic Volume count survey
Axle Load Survey
Origin & Destination survey
Intersection Volume Count (Turning movement survey)
Speed-Delay Survey
2.2 | Collection of Petrol pump selling Data
2.3 | Preparation of Traffic Report
2.4 | Geometric Design for various Alignment options
2.5 | Collection of Cadastral Maps & Revenue records etc.
2.6 | Collection of Survey of India (SOI) Maps
2.7 | Collection of Reserved Forest Survey nos. and Protected Forest Chainage from concern DCF
2.8 | Walkthrough on proposed new greenfield alignment/Bypass/Realignment /Existing alignment
2.9 | Public Consulation incl. consultation with Communities, Working NGOs & other stake-holders
2.10 | Final Geometric Design for various Alignment options
2.11 | Submission of Alignment Options Report with presetation
2.12 | Approval of Alignment / Comments of Client on Alignment Options Report
2.13 | Submission of Final Alignment Report
2.14 | Approval of Final Alignment Report
2.15 | Exisitng Road Condition survey / NSV Survey (incl. Road inventory)
2.16 | Collection of Existing Sub-Grade Soil Sample & Testing / Trial pit investigation
2.17 | Pavement Structural Strenth Survey / FWD Test
2.18 | Pavement Design Analysis (With Different Options)
2.19 | Collection of Accident data (FIR) for Identification of Black Spots / Black Spots Audit report
2.20 | Existing Bridges, Culverts & Structures Condition survey
2.21 | Collection & Testing of Various materials & Other locally availabe material / Material
2.22 | Submission of Draft Feasibility Report (for Alignment recommend by DPR consultant)
2.23 | Comments of Client on Draft FS Report
2.24 | Submission of Final Feasibility Report
2.25 | Approval of Final Feasibility Report
3 | LA & Clearance -I Report
3.1 | LA
3.2 | Publication of 3a / 10a Gazette Notification
3.3 | Preparation of Draft 3A / 11 Notifications (Eligible for 1% Bonus)
3.4 | Preparation of Estimated Cost of Land Acquisition
3.5 | Preparation of Strip / LA Plan
3.6 | Submission of Draft LA -I Report
3.7 | Comments of Client on Draft LA -I Report
3.8 | Submission of Final LA -I Report
3.9 | Approval of Final LA -I Report
3.10 | Utility
3.11 | Identification of surface utilities (Field Study)
3.12 | Identification of sub-surface utilities (Field Study) / GPR Survey
3.13 | Identification of Tentative Cost of relocation
3.14 | Submission of Utility Shifting proposals to user agency
3.15 | Submission of Utility Shifting proposals - LT Lines
3.16 | Submission of Utility Shifting proposals - HT Lines
3.17 | Submission of Utility Shifting proposals - EHT Lines
3.18 | Submission of Utility Shifting proposals - Water Pipeline
3.19 | Submission of Utility Shifting proposals - Sewage Line
3.20 | Submission of Utility Shifting proposals - Storm Water Line
3.21 | Submission of Utility Shifting proposals - Hand Pumps
3.22 | Submission of Utility Shifting proposals - OFC Line
3.23 | Submission of Utility Shifting proposals - Telephone Cable Line
3.24 | Submission of Utility Shifting proposals - GAS Line
3.25 | Submission of Utility Shifting proposals - CNG Line
3.26 | Submission of Utility Shifting proposals - Petrolium Line
3.27 | Submission of Utility Shifting proposals - Gantry Board
3.28 | Submission of Utility Shifting proposals - Hoarding Board
3.29 | Submission of Utility relocation/ Utility plan with Detailed Utility statement
3.30 | Clearance
3.31 | Initial consultation with competent authority
3.32 | Submission of Clearance proposals - Protected Forest
3.33 | Submission of Clearance proposals - Reserved Forest
3.34 | Submission of Clearance proposals - FRA Certificate
3.35 | Submission of Clearance proposals - Environment Clearance
3.36 | Submission of Clearance proposals - Wildlife Clearance
3.37 | Submission of Clearance proposals - CRZ Clearance
3.38 | Submission of Clearance proposals - Inlandwater Clearance
3.39 | Submission of Clearance proposals - Railway Clearance /GAD Submission
3.40 | Submission of Clearance proposals - Irrigation Clearance /GAD Submission
3.41 | Submission of Clearance proposals - Archeology Clearance -State protected
3.42 | Submission of Clearance proposals - Archeology Clearance-Central protected
3.43 | Submission of Clearance proposals - NHAI /GAD Submission
3.44 | Submission of Clearance proposals - State PWD/GAD Submission
3.45 | Submission of Clearance proposals - Panchayat /GAD Submission
3.46 | Submission of Clearance proposals - Local Govt. Body/GAD Submission
3.47 | Submission of Clearance proposals - R&B Design Circle (Span>60m)
3.48 | Submission of Clearance proposals - NIT (GAD Submission) (Span<= 60m)
3.49 | Submission of Clearance -I Report
4 | Detailed Project Report
4.1 | Detailed Topographic Survey (on Approved alignment / Deemed to be approved alignment)
4.2 | Draft Plan - Profile Design of Highway (FRL as per Utility shifting owner need & Clearances need)
4.3 | Finalised Proposed Strcuture list (Nos., Type, Span etc) (Inconsultation with Soil/Design/Hyd-RS wall dept.)
4.4 | Hydraulic & Hydrological Investigation report
4.5 | Geo-technical and sub-soil explorations report (Nos.of GT Inconsultation with Soil & Project Team)
4.6 | Final Plan - Profile Design of Highway (Inconsultation Design dept.) (with Prior approval of client)
4.7 | Preparation of Detialed Estimate of Highway (incl. Final TCS & Lane Configuration)
4.8 | Preparation of Proposed Structures GADs
4.9 | Preparation of Detialed Estimate of Proposed Structures
4.10 | Preparation of Design Based Report (DBR) (Road and strutuers)
4.11 | Preparation of Misc. Drawings ( Road furniture plan, Junction improvement etc..)
4.12 | Preparation of Drainage Design Report
4.13 | Preparation of Drainage plan
4.14 | Economic and financial analysis report
4.15 | Environmental Assessment Report including Environmental management Plan (EMP)
4.16 | Socio Economic impact Study (Initial social assessment/ preliminary LA resettlement plan) Resettlement Action Plan (RAP)
4.17 | Submission of Draft Detailed Project Report (on Approved Alignment)
4.18 | SFC Presentaion and DPR Presentation
4.19 | Comments of Client on Draft DPR
4.20 | Submission of Final Detailed Project Report
4.21 | Approval of Final Detailed Project Report
5 | Civil work contract Agreement & Technical Schedule
5.1 | Preparation of Technical Schedule (A,B,C,D) (Need for SFC..)
5.2 | Submission of Draft Civil work contract Agreement with technical schedule
5.3 | Submission of Bid Documents (RFP / NIT etc..)
5.4 | Comments of Client on Draft Civil work contract Agreement with technical schedule
5.5 | Submission of Bid Documents & Civil work Contract Agreement incl. Technical Schedule
5.6 | Approval of Bid Documents & Civil work Contract Agreement incl. Technical Schedule
5.7 | Prebid Query Reply
5.8 | Packgae Award to Concessionaire/Contractor
6 | LA & Clearance II Report
6.1 | LA
6.2 | Publication of 3A / 11 Gazette Notification
6.3 | Fixing of Boundary pillar for PROW marking & Centre line marking
6.4 | Joint measurement survey with DILR officials / competent authority
6.5 | Valuation of existing properties atteched with the acquistion land
6.6 | Publication of 3D Gazette Notification
6.7 | Preparation of Final Strip / LA Plan
6.8 | Submission of LA -II Report
6.9 | Utility
6.10 | Joint site inspection with competent authority
6.11 | Submission of Utility Shifting Estimates / Quotation with NO upgradation certificate
6.12 | - LT Lines
6.13 | - HT Lines
6.14 | - EHT Lines
6.15 | - Water Pipeline
6.16 | - Sewage Line
6.17 | - Storm Water Line
6.18 | - Hand Pumps
6.19 | - OFC Line
6.20 | - Telephone Cable Line
6.21 | - GAS Line
6.22 | - CNG Line
6.23 | - Petrolium Line
6.24 | - Gantry Board
6.25 | - Hoarding Board
6.26 | Approval of Utility Shifting Estimates / Quotation
6.27 | Submission Final Utility relocation plan with Detailed Utility statement
6.28 | Submission of Utility-II Report
6.29 | Clearance
6.30 | Clearance approval - Protected Forest (Stage-1)
6.31 | Clearance approval - Protected Forest (Stage-2)
6.32 | Clearance approval - Reserved Forest (Stage-1)
6.33 | Clearance approval - Reserved Forest (Stage-2)
6.34 | Clearance approval - Environment Clearance
6.35 | Clearance Approval - Wildlife Clearance
6.36 | Clearance Approval - CRZ Clearance
6.37 | Clearance Approval - Inlandwater Clearance
6.38 | Clearance Approval - Railway Clearance / GAD Approval
6.39 | Clearance Approval - Irrigation Clearance / GAD Approval
6.40 | Clearance Approval - Archeology Clearance -State protected
6.41 | Clearance Approval - Archeology Clearance-Central protected
6.42 | Clearance Approval - NHAI / GAD Approval
6.43 | Clearance Approval - State PWD / GAD Approval
6.44 | Clearance Approval - Panchayat / GAD Approval
6.45 | Clearance Approval - Local Govt. Body / GAD Approval
6.46 | Clearance Approval - R&B Design Circle (Span>60m)
6.47 | Clearance Approval - NIT (GAD Submission) (Span<= 60m)
6.48 | Submission of Final Clearance-II Report
7 | Land Award Report (LA-III Report)
7.1 | Award Decleration (3G)
7.2 | Submission of Land Award Report
8 | Land possession Report (LA-IV Report)
8.1 | Deposition of compensation amount by Govt. to CALA 3(H)
8.2 | Disbursement to Land owners by CALA
8.3 | Receipt of Land Possession Certificate 3 ( E)
8.4 | Submission of Land possession Report

## Stage Report (hidden)
Detailed Project Report / PMC Report Submission and Approval Authority
Stage | Report |  | % Payment Schedule | Approved by | Remark
- | Monthly Progress Report (MPR) |  | - | - | -
1 | ▪ Inception report & ▪ QAP Documents |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist-Feb-24 Stage-1 (Pavement / Structure)
2 | Feasibility Report including alignment option study | ▪ Volume-I : Alignment Option Report ▪ Volume-II : Fesibility Report - Main Report (Appendix-1 : Traffic Report) (Appendix-2 : NSV Report incl. Road inventory) (Appendix-3 : FWD Report) (Appendix-4 : Pavement Design Report with Design options) (Appendix-5 : Economic and financial analysis report) (Appendix-6 : Black spot report) (Appendix-7 : Existing structures Inventory & Condition survey Report) (Appendix-8 : Geo Technical investigation Report) (Appendix-9 : Hydraulic Report) (Appendix-10 : Material Report) (Appendix-11 : Environment and Social Impact Assessment report) (Appendix-12 : Rate analysis) (Appendix-13 : Block Estimate) (Appendix-14 : Preliminary land acquisition Details) (Appendix-15 : Alignment Drawing (P&P,TCS only) | 10% | AS/ADG/CE-cordinator, MoRT&H | Alignment option report may be submit some time seperately (Point-16) Follow DPR checklist-Feb-24 Stage-2 (Pavement / Structure)
3 | LA & Clearance I Report | ▪ LA-I Report & Strip Plan with Estimated Cost of LAQ | 5% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist -Feb-24 Stage-3 (Pavement / Structure)
|  | ▪ Utility-I Report incl. Utility relocation plan | 2.5%
|  | ▪ Clearance-I Report | 5%
4 | Detailed Project Report (DPR) | ▪ Draft / Final Detailed Project report Volume-I : Main Report Volume-II : Design Report (Part-1 : Road - DBR & Appendix-1 to 6) (Part-2: Structure -DBR & Appendix-7 to 9) Volume-III : Material Report Volume-IV : Environmental & Social impact Assessment Report Volume-V : Technical Specifications Volume-VI : Rate Analysis Volume-VII : Detailed Estimate Volume-VIII : & BOQ Volume-IX : Drawing Volume-X : Drainage Plan (Part-1 : Drainage Design report) (Part-2: Drawings) | 10% | AS/ADG/CE-cordinator, MoRT&H | Follow DPR checklist -Feb-24 Stage-4 (Pavement / Structure)
5 | Civil work contract agreement along with Technical Schedule & Bid Documents |  | 15% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist -Feb-24 Stage-5 (Pavement / Structure)
6 | LA & Clearance II Report | ▪ LA-II Report & Final Strip Plan & Cost of LAQ | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist -Feb-24 Stage-6 (Pavement / Structure)
|  | ▪ Utility-II Report incl. Final Utility relocation plan | 2.5%
|  | ▪ Clearance-II Report | 5%
7 | Award Determination Report / LA & Clearance III Report |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist -Feb-24 Stage-7 (Pavement / Structure)
8 | Land Possession Report / LA & Clearance IV Report |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H | Follow DPR checklist -Feb-24 Stage-8 (Pavement / Structure)
- | Aftrer 3 year from work start & Project COD whichever is earlier |  | 5% | - | -

## Approval Authority GDR (hidden)
REPORTS FOR DPR & APPROVAL AUTHORITY (GDRPL)
Sr. No. | Type of Report | Approved By
1 | Monthly Progress Report | Zulfikar Petiwala
2 | Draft / Final Inception Report & QAP | Zulfikar Petiwala
3 | Alignment Options Report / Final Alignment report | Krunal Patel
4 | Draft / Final Feasibility Report
4.1 | Main Report (Feasibility) | Zulfikar Petiwala
4.2 | Traffic Report | Krunal Patel
4.3 | NSV Report | Zulfikar Petiwala / Ritesh
4.4 | FWD Report | Zulfikar Petiwala / Ritesh
4.5 | Pavement Design Report (With alternative Design Options) | Krunal Patel
4.6 | Black Spot Report / Safety Audit report (DPR Stage) | Hemant Pandya / Aditya Pancholi
4.7 | Existing Structures Inventory & Condition survey report | Nilay Gandhi
4.8 | Material Report | Krunal Patel / Zulfikar Petiwala
4.9 | Block Estimate | Zulfikar Petiwala
4.1 | Drawings (P&P, TCS only) | Zulfikar Petiwala
5 | LA & Clearance I Report
5.1 | LA & Clearance I Report | Zulfikar Petiwala
5.2 | 3(a) Gazzete Notification & Submission of 3(A) / 10A Proposal | Zulfikar Petiwala/Ramesh Vanzara
5.3 | Strip Plan / LA Plan and Estimated cost of Land Acquisition | Zulfikar Petiwala/Ramesh Vanzara
5.4 | Submission of Utility Shifting Proposal | Zulfikar Petiwala
5.5 | Utility Shifting plan with Detailed Utility statement | Zulfikar Petiwala
5.6 | Submission of Necessary Clearance Proposal | Zulfikar Petiwala
6 | Draft / Final Detailed Project Report (DPR)
6.1 | Main Report (Detailed Project Report) | Zulfikar Petiwala
6.2 | Design Base Report - Road | Krunal Patel / Zulfikar Petiwala
6.3 | Pavement Design Report (With Final Design among all Options) | Krunal Patel
6.4 | Economic and financial analysis report | Krunal Patel / Zulfikar Petiwala
6.5 | Design Base Report - Structure | Nilay Gandhi/Fakhruddin
6.6 | Geo Technical Investigation report | Vishal Sakpal
6.7 | Hydraulic & Hydrological Investigation report | Suresh Jain
6.8 | Environmental Assessment Report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP): | Zulfikar Petiwala / Toshit
6.9 | Techincal Specification (Special technical specifications which are not covered by MOST Specifications) | Zulfikar Petiwala / Krunal Patel | Peer-reviewed by a panel of GDRPL reviewers
6.1 | Drainage Design Report | Krunal Patel
6.11 | Rate Analysis | Zulfikar Petiwala
6.12 | Detailed Estimate | Zulfikar Petiwala
6.13 | Drawing Volume
| Highway : Keyplan, Index, Hori. & Vert. Curve Table, LSR, Centreline Coordinate, TBM List, Lane configuration/TCS Schedule, Typical cross sections, Plan-Profile, Road furniture plan, Junction improvement Drawing etc…. | Krunal Patel / Zulfikar Petiwala
| Structure : GADs, Protection work (Retaining wall/Toe wall/Gabion/Breast wall, Crash barrier etc…. | Nilay Gandhi/Fakhruddin
| Project Facility : Toll Plazas, Rest Area, Bus bays, Truck lay buys etc.... | Zulfikar Petiwala
| Drainage plan | Krunal Patel / Zulfikar Petiwala
7 | Bid documents and civil works contract agreement along with technical schedules | Zulfikar Petiwala / Vishal Sakpal in Consultation with Krunal Patel
8 | LA & Clearance II Report
8.1 | LA & Clearance II Report | Zulfikar Petiwala
8.2 | 3(A) & 3(D) Gazzete Notification OR Publication of Section 10A, 11 & 19 | Zulfikar Petiwala/Ramesh Vanzara
8.3 | Final Strip Plan / LA Plan and Final Estimated cost of Land Acquisition | Zulfikar Petiwala/Ramesh Vanzara
8.4 | Submission of Utility Shifting Estimates | Zulfikar Petiwala
8.5 | Final Utility Shifting plan with Detailed Utility statement | Zulfikar Petiwala
8.6 | NO Upgradation Certificate | Zulfikar Petiwala
8.7 | Submission of Final clearances Documents/Drawings received by competent authority | Zulfikar Petiwala
9 | LA & Clearance III Report / Award Determination Report | Zulfikar Petiwala/Ramesh Vanzara
10 | LA & Clearance IV Report / Land Possession Report | Zulfikar Petiwala/Ramesh Vanzara

## Approval Authority .
DPR REPORT CHECKLIST
Sr. No. | Type of Report | Prepared By | Checked By | GDRPL Approval by |  | % Payment Schedule | Client Approval by
0 | Monthly Progress Report | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala |  | -- | --
1 | Inception Report & QAP | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
2 | Feasibility Report | [5 empty] | AS/ADG/CE-cordinator, MoRT&H
2.1 | ▪ Volume-I : Alignment Option Report | Highway Enginner | Project Co-Ordinator | Krunal Patel |  | 10%
2.2 | ▪ Volume-II : Fesibility Report - Main Report |  | Project Co-Ordinator | Zulfikar Petiwala
| Appendix-1: Traffic Report |  |  | Krunal Patel
| Appendix-2: NSV Report incl. Road inventory |  |  | Zulfikar Petiwala / Ritesh
| Appendix-3: FWD Report |  |  | Zulfikar Petiwala / Ritesh
| Appendix-4: Pavement Design Report (With alternative Design Options) |  |  | Krunal Patel
| Appendix-5: Economic and financial analysis report |  |  | Krunal Patel / Zulfikar Petiwala
| Appendix-6: Black Spot Report / Safety Audit report (DPR Stage) |  |  | Hemant Pandya / Aditya Pancholi
| Appendix-7: Existing Structures Inventory & Condition survey report |  |  | Nilay Gandhi / Fakhruddin
| Appendix-8: Geo Technical Investigation report |  |  | Vishal Sakpal
| Appendix-9: Hydraulic & Hydrological Investigation report |  |  | Suresh Jain
| Appendix-10: Material Report |  |  | Krunal Patel / Zulfikar Petiwala
| Appendix-11: Environmental Assessment Report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP): |  |  | Seema medam
| Appendix-12: Rate Analysis |  |  | Zulfikar Petiwala
| Appendix-13: Block Estimate |  |  | Zulfikar Petiwala
| Appendix-14: Preliminary land acquisition Details |  |  | Zulfikar Petiwala/Ramesh Vanzara
| Appendix-15: Alignment Drawings (P&P, TCS only) |  |  | Zulfikar Petiwala
3 | LA & Clearance I Report | [5 empty] | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
3.1 | ▪ Volume-I : LA I Report | TA (C) | Project Co-Ordinator | Zulfikar Petiwala |  | 5%
| Appendix-1: 3(a) Gazzete Notifications & 3(A) / 10A Proposal | LAC |  | Zulfikar Petiwala/Ramesh Vanzara
| Appendix-2: Strip Plan / LA Plan | LAC |  | Zulfikar Petiwala/Ramesh Vanzara
| Appendix-3: Estimated cost of Land Acquisition | TA (C) |  | Zulfikar Petiwala
3.2 | ▪ Volume-II: Utility I Report | TA (U) | Project Co-Ordinator | Zulfikar Petiwala |  | 2.5%
| Appendix-1: Submission of Utility Shifting Proposal | TA (U) |  | Zulfikar Petiwala
| Appendix-2: Utility Shifting plan with Detailed Utility statement | TA (U) |  | Zulfikar Petiwala
3.3 | ▪ Volume-III: Clearance I Report | TA (C) | Project Co-Ordinator | Zulfikar Petiwala |  | 5%
| Appendix-1: Submission of Necessary Clearance Proposal | TA (C) |  | Zulfikar Petiwala
4 | Draft / Final Detailed Project Report (DPR) | [5 empty] | AS/ADG/CE-cordinator, MoRT&H
4.1 | Volume-1: Main Report | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala |  | 10%
4.2 | Volume-2: Design Report |  | Project Co-Ordinator | Krunal Patel / Zulfikar Petiwala
| Part-1: Design Base Report - Road |  | Project Co-Ordinator | Zulfikar Petiwala
| Appendix-1: Traffic Report |  |  | Krunal Patel
| Appendix-2: NSV Report incl. Road inventory |  |  | Zulfikar Petiwala / Ritesh
| Appendix-3: FWD Report |  |  | Zulfikar Petiwala / Ritesh
| Appendix-4: Pavement Design Report (With Final Design among all Options) |  |  | Krunal Patel
| Appendix-5: Economic and financial analysis report |  |  | Krunal Patel / Zulfikar Petiwala
| Appendix-6: Black Spot Report / Safety Audit report (DPR Stage) |  |  | Hemant Pandya / Aditya Pancholi
| Part-2: Design Base Report - Structure |  |  | Nilay Gandhi / Fakhruddin
| Appendix-7: Existing Structures Inventory & Condition survey report |  |  | Nilay Gandhi / Fakhruddin
| Appendix-8: Geo Technical Investigation report |  |  | Vishal Sakpal
| Appendix-9: Hydraulic & Hydrological Investigation report |  |  | Suresh Jain
4.3 | Volume-3: Material Report |  |  | Krunal Patel / Zulfikar Petiwala
4.4 | Volume-4: Environmental Assessment Report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP): |  |  | Seema medam
4.5 | Volume-5: Techincal Specification (Special technical specifications which are not covered by MOST Specifications) |  |  | Zulfikar Petiwala / Krunal Patel | Peer-reviewed by a panel of GDRPL reviewers
4.6 | Volume-6: Rate Analysis |  |  | Zulfikar Petiwala
4.7 | Volume-7: Detailed Estimate |  |  | Zulfikar Petiwala
4.8 | Volume-8: BOQ |  |  | Zulfikar Petiwala
4.9 | Volume-9: Drawings |  |  | Zulfikar Petiwala
| Part-1 : Highway : Keyplan, Index, Hori. & Vert. Curve Table, LSR, Centreline Coordinate, TBM List, Lane configuration/TCS Schedule, Typical cross sections, Plan-Profile, Road furniture plan, Junction improvement Drawing etc…. |  |  | Krunal Patel / Zulfikar Petiwala
| Part-2 : Structure : GADs, Protection work (Retaining wall/Toe wall/Gabion/Breast wall, Crash barrier etc…. |  |  | Nilay Gandhi/Fakhruddin
| Part-3 : Project Facility : Toll Plazas, Rest Area, Bus bays, Truck lay buys etc.... |  |  | Zulfikar Petiwala
4.1 | Volume-10: Drainage Design Report |  |  | Krunal Patel
| Appendix-10: Drainage plan |  |  | Krunal Patel / Zulfikar Petiwala
5 | Bid documents and civil works contract agreement along with technical schedules | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala / Vishal Sakpal in Consultation with Krunal Patel |  | 15% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
6 | LA & Clearance II Report | [5 empty] | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
6.1 | ▪ Volume-I : LA II Report | TA (C) | Project Co-Ordinator | Zulfikar Petiwala |  | 10%
| Appendix-1: 3(A) & 3(D) Gazzete Notification OR Publication of Section 10A, 11 & 19 | LAC |  | Zulfikar Petiwala/Ramesh Vanzara
| Appendix-2: Final Strip Plan / LA Plan | LAC |  | Zulfikar Petiwala/Ramesh Vanzara
| Appendix-3: Final Estimated cost of Land Acquisition | LAC |  | Zulfikar Petiwala
6.2 | ▪ Volume-II: Utility II Report | TA (U) | Project Co-Ordinator | Zulfikar Petiwala |  | 2.5%
| Appendix-1: Submission of Utility Shifting Estimates | TA (U) |  | Zulfikar Petiwala
| Appendix-2: Final Utility Shifting plan with Detailed Utility statement | TA (U) |  | Zulfikar Petiwala
| Appendix-3: NO Upgradation Certificate | TA (U) |  | Zulfikar Petiwala
6.3 | ▪ Volume-III: Clearance II Report | TA (C) | Project Co-Ordinator | Zulfikar Petiwala |  | 5%
| Appendix-1: Submission of Final clearances Documents/Drawings received by competent authority | TA (C) |  | Zulfikar Petiwala
7 | LA & Clearance III Report / Award Determination Report | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala/Ramesh Vanzara |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
8 | LA & Clearance IV Report / Land Possession Report | Highway Enginner | Project Co-Ordinator | Zulfikar Petiwala/Ramesh Vanzara |  | 10% | CE, PWD / CE, BRO in Consulation with RO,MoRT&H
- | Aftrer 3 year from work start & Project COD whichever is earlier | -- |  | -- |  | 5% | --
* NOTE: Follow DPR checklist-Feb-24 Stage-1 to 8 (Pavement / Structure) for respective Report and atteched Checklist in Report

## DPR activity
Detailed Activity Checklist for DPR Projects
1. Project Management
1.1 | Award of Project (Receiving LOA)
1.2 | Submission of Performance security / Bank Guarantee
1.3 | Signing the Tender Agreement
1.4 | Kick-off Meeting with client & preliminary site visit
1.5 | Letter for work execution (Receiving Work order)
1.6 | Monthly Progress report (By 5th of Every Month)
1.7 | Time limit Extenstion and Excess approval, if any.
2. Reconnaissance Survey
2.1 | Exisitng Road Inventory survey as per IRC:SP:19
2.2 | Inventory for Exisitng CD Structure, Bridges, Structures as per IRC:SP:35
2.3 | Exisitng Pavement condition/Composition survey as per IRC:SP:19
2.4 | Condition Survey for Exisitng CD Structure, Bridges, Structures as per IRC:SP:35
2.5 | Public Consulation including consultation with Communities located along the road, NGOs working in the area & other stake-holders
2.6 | Environment and Social Impact Assessment
2.7 | Videography of entire highway stretch
2.8 | Walkthrough on proposed new greenfield alignment/Bypass/Realignment/Existing alignment
3. Collection from field / Data Preparation
3.1 | Collection of Soil Sample by Digging test Pits along road alignment (For In-situ physical properties, Laboratory physical properties, Chemical Properties etc)
3.2 | Collection of Various materials (e.g. Cement, Steel, Aggregates, Bitumen, Emulsion, Borrow area soil, Water sample etc)
3.3 | Collection of Accident data (FIR) from the Police Station / Black spot locations
3.4 | Collection of Maps & Land revenue records etc.
3.5 | Collection of Reserved Forest Survey nos. and Protected Forest Chainage from concern DCF office / collect government notifications declaring forest land as PF/RF and its maps.
3.6 | Collection of utility shifting estimates/Quotations from all user agencies
3.7 | DPR Data Sheets Preparaion (For Final Approved Alignment)
Lane Configurations Sheet , Structure list, Existing & Proposed Final ROW List, Village Boundary List, Bus Bay & Truck Lay Bye List, Terrain & Builtup areas list, Junction List with improvement details etc
3.8 | Technical Note
4. Surveys at Site
4.1 | Traffic survey & Analysis
Classified Traffic Volume count survey
Axle Load Survey
Origin & Destination survey (Passengers & Goods trips)
Intersection Volume Count (Turning movement survey)
Speed-Delay Survey
Analysis on Pedestrian / Animal flow characteristics
Truck Terminal survey
4.2 | Existing Pavement Structural Strenth using FWD as per IRC:115 (Flexible) & IRC:117 (Rigid)
4.3 | Existing Pavement Roughness Tests IRC:SP:16 / Roughness using Laser Profilometer by NSV
4.4 | Detailed Topographic Survey on approved alignment Using DGPS & Total Station / Drone LiDAR or better technology
4.5 | Ground Penetrating Radar (GPR) Survey for detection of sub-surface utilities
4.6 | Geo-technical and sub soil Exploration at Existing/proposed structures as per IRC:78
4.7 | Joint Measurement survey with utilities owning agencies (Govt.)
4.8 | Fixing of Boundary pillar for PROW marking & Centre line marking
4.9 | Joint Measurement survey with DILR officials for forest clearance
4.1 | Joint Measurement survey with Govt. Valuer for valuation of demolish structures
4.11 | Joint Site Visit with Concern Forest officials of Reserved forest for Punchnama of the proposed diversion & marking kharda of trees to be cut.
4.12 | Joint Site Visit with Concern Forest officials of Protected forest for Punchnama of the proposed diversion & marking kharda of trees to be cut.
5. Detailed Design
5.1 | Geometric Design of a Existing alignment
5.2 | Draft Geometric Design of a proposed alignment (Plan & Profile Drawings)
5.3 | Hydraulic & Hydrological Investigation for proposed structures as per IRC:SP:13 & IRC:5
5.4 | Final Geometric Design of a proposed alignment (Plan & Profile Drawings)
5.5 | Intersections, Grade separators & Interchanges with ramps
5.6 | Typical Cross section Design & Drawings
5.7 | Road Safety Furniture Drawings incl. Road Signs, Pavement marking, Safety barrier, Railings, Delineators, Chevron markings, Traffic attenuators, Crash barriers, overhead signs etc
5.8 | Preparation of GAD of Proposed structures
5.9 | Roadside Drain Design & Drawings (RCC / Earthen)
5.1 | Protection work Design & Drawings (Toe wall /Retaining Wall / Brest wall / RE wall etc..)
5.11 | Arboriculture and Landscaping Design & Drawings
5.12 | Toll Plaza Design Design & Drawings(Incl.Weighing Station, Parking Areas etc.)
5.13 | Rest Area Design & Drawings
5.14 | Bus Bay, Truck Lay Bye Pedestrian crossing etc design & Drawings
6. Report Preparation & Submissions
6.1 | Draft / Final Inception Report & QAP
6.2 | Alignment Options Report / Final Alignment report
6.3 | Draft / Final Feasibility Report
Traffic Surveys Analysis & Report
Accident Analysis Report (Identification of black spots on project stretch)
Environmental Impact Assesement Study (Land, Air, Water resources, Noise & Biological envirnmental details / impact / mitigation measures ) including Environmental management Plan
Socio Economic impact Study including Resettlement Action Plan (RAP)
Alignment Options study with merits & demerits
Cost Estimate with Rate Analysis
Normative Cost
Life cycle cost analysis
Economical Internal Rate of Return (EIRR) report as per IRC:SP:30
Financial Internal Rate of Return (FIRR) report
6.4 | Draft / Final Detailed Project Report (DPR)
Material Report
Pavement Design Report
Design Base Report - Structures / Final road Alignment / Drain
Hydraulic Design report - Structures / Road Side Drain (Earthen & RCC )
Geotechnical Investigation Report
Environmental Assesement Report
Detailed Bills of Quantities (BOQ) with rate analysis
6.5 | Draft / Final LA & Clearance I Report
LAQ/ Utility/ Environment/Forest/Wild life/CRZ/ Railway/Irrigation/Other concerned Dept. clearance Necessity, identifications and relevant details including Land acquisition 3a & 3A Draft Notifications (or Section-11)
LA/Strip Plan
Estimated cost of land acquisition
Utility relocation plan incl. Details of properties / Utilities
Cost of Utility Shifting
6.6 | Draft / Final LA & Clearance II Report
Environment/Forest/Wild life/ Utility/ Railway/ Irrigation /Other concerned Dept. clearances Approval details including Land acquisition 3a & 3A Gazette Notifications (or Section-11) & 3D Gazette Notifications (or Section-19))
6.7 | Valuations of structures need to be demolish
6.8 | Draft / Final LA & Clearance III Report
Land Award report (Completion of award declaration (3G) for 90% of land parcels identified in LA II report)
6.9 | Draft / Final LA & Clearance IV Report
Land Possession report Receipt of land possession certificates (3E) for 90% of all land parcels identified in LA III report)
6.1 | Bid documents (RFP) and civil works contract agreement along with technical schedules (EPC/HAM)
7. Approval from Authority
7.1 | Draft Inception Report & QAP (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
7.2 | Final Inception Report & QAP
7.3 | Draft Feasibility Report (Approved By: AS/ADG/CE-cordinator, MoRT&H)
7.4 | Alignment Options Report
7.5 | Alignment Approval (Approved By: AS/ADG/CE-cordinator, MoRT&H)
7.6 | Final Feasibility Report
7.7 | Final Alignment Report
7.8 | Draft Detailed Project Report (DPR) (Approved By: AS/ADG/CE-cordinator, MoRT&H)
7.9 | Final Detailed Project Report (DPR)
7.1 | LA & Clearance I Report (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
7.11 | LA & Clearance II Report (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
7.12 | LA & Clearance III Report (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
7.13 | LA & Clearance IV Report (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
7.14 | Bid documents and civil works contract agreement along with technical schedules (Approved By: CE, PWD / CE, BRO in Consulation with RO,MoRT&H)
8. Clearances
8.1 | FRA Certificate (Reserved & Protected Forest)
8.2 | Protected Forest Clearances
8.3 | Reserved Forest Clearances
8.4 | Utility shifting estimate / Quotation
8.5 | Other Clearances, if any
Final GAD approval of ROB from concern Chief Bridge Engineer (Railway)
NOC from concern Irrigation department
NOC from concern NHAI/R&B/NHIDCL/PWD/BRO etc.
NOC from concern Wild life department
NOC from concern Archeology department
NOC from concern CRZ
Approval of Environment Clearance (EC)
* | FRA Certificate
Submission of PF/RF proposal to collector
Submission of PF/RF proposal from collector to SDM
Submission of PF/RF proposal from SDM to Prayojna Vahivatdar office
Approval of of PF/RF proposal & Recommendation for issue FRA Certificate from Prayojna Vahivatdar office to SDM
Approval of of PF/RF proposal & Recommendation for issue FRA Certificate from SDM to Collector
Issue FRA Certificate of PF/RF by Collector
* | Forest Clearances
Submission of Online proposal by user agency to Concern DCF, Division office (Form-A, Part-1)
Submission of Proposal in Physical file by user agency to Concern DCF, Division office
Submission of field visit report with Punchnama & Marking Kharda by RFO in DCF, Division office
Submission of Online proposal & Physical files by DCF to concern CCF,circle office (Form-A, Part-2)
Submission of Online proposal & Physical files by CCF to Nodal office (APCCF) (Form-A, Part-3)
Submission of Physical files to PCCF(HoFF)
Submission of Online proposal & Physical files by Nodal office (APCCF) to Secretary-(F&ED) (Form-A, Part-4)
Submission of Physical files to Hon’ble. MoS and Hon’ble Cabinet Minister
Online submission of Proposals and submission of physical file to APCCF-Regional Office, Western Zone-Bhopal
Online submission of Proposals and submission of physical file to RO (HQ) new Delhi
Principle Approval by APCCF-Regional Office, Western Zone-Bhopal (<40 Ha.) / RO (HQ) new Delhi
Demand Note for payment of NPV and compliance report
Apply for obtaining the Demand Note for NPV.
Processing for Payment of NPV by User Agency.
To apply to get Demand Note for C.A. Scheme for double degraded forest area or to hand over land bank to Forest Department and to get C.A. Scheme to pay to Forest Department.
To prepare compliance report and submit to concern DCF.
Persual for obtaining Working Permission
Submission of Compliance Report to CCF.
Submission of compliance report to Nodal Officer.
Submission of compliance report to PCCF.
Submission of compliance report to Secretary-F&ED.
Submission of compliance report to Regional Office/MoEF
Perusal for final Permission at Regional Office (Stage-II Approval & Memorandum)
Pursue Regional Office/MoEF for getting final approval.
Application to Obtain Government Notification. (Memorandum)
Application for Removal of Trees at Division Level

## Checklist
DPR REPORTS & APPROVAL AUTHORITY |  | DPR REPORTS & APPROVAL AUTHORITY | [7 empty] | DPR REPORTS & APPROVAL AUTHORITY | [7 empty] | DPR REPORTS & APPROVAL AUTHORITY | [6 empty] | DPR REPORTS & APPROVAL AUTHORITY
Sr. No. | Type of Report | NH8C | Kerala NH766 | Pardi Kaprada NH848 | Khokhra NH58 | VUDA TP-22 PMC | Rajpipla bypass | Palanpur bypass | VUDA Ring Road PMC | Andhra NH216 PMC | Coimbatore | Madurai Bypass | Nagaland PMC | Surat - Sachin | Navsari | Vadodara - SOU | Assam NH427 PMC | Ank-Rajpipla | Porbandar | Amod Dahej | VUDA Flyover PMC | NH 329A PMC | VUDA Green Road PMC | NH 64
0 | Monthly Progress Report
1 | Inception Report & QAP
2 | Feasibility Report
2.1 | ▪ Volume-I : Alignment Option Report
2.2 | ▪ Volume-II : Fesibility Report - Main Report
Appendix-1: Traffic Report
Appendix-2: NSV Report incl. Road inventory
Appendix-3: FWD Report
Appendix-4: Pavement Design Report (With alternative Design Options)
Appendix-5: Economic and financial analysis report
Appendix-6: Black Spot Report / Safety Audit report (DPR Stage)
Appendix-7: Existing Structures Inventory & Condition survey report
Appendix-8: Geo Technical Investigation report
Appendix-9: Hydraulic & Hydrological Investigation report
Appendix-10: Material Report
Appendix-11: Environmental Assessment Report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP):
Appendix-12: Rate Analysis
Appendix-13: Block Estimate
Appendix-14: Preliminary land acquisition Details
Appendix-15: Alignment Drawings (P&P, TCS only)
3 | LA & Clearance I Report
3.1 | ▪ Volume-I : LA I Report
3.2 | Appendix-1: 3(a) Gazzete Notifications & 3(A) / 10A Proposal
3.3 | Appendix-2: Strip Plan / LA Plan
3.4 | Appendix-3: Estimated cost of Land Acquisition
3.5 | ▪ Volume-II: Utility I Report
3.6 | Appendix-1: Submission of Utility Shifting Proposal
3.7 | Appendix-2: Utility Shifting plan with Detailed Utility statement
3.8 | ▪ Volume-III: Clearance I Report
3.9 | Appendix-1: Submission of Necessary Clearance Proposal
4 | Draft / Final Detailed Project Report (DPR)
4.1 | Volume-1: Main Report
4.2 | Volume-2: Design Report
Part-1: Design Base Report - Road
Appendix-1: Traffic Report
Appendix-2: NSV Report incl. Road inventory
Appendix-3: FWD Report
Appendix-4: Pavement Design Report (With Final Design among all Options)
Appendix-5: Economic and financial analysis report
Appendix-6: Black Spot Report / Safety Audit report (DPR Stage)
Part-2: Design Base Report - Structure
Appendix-7: Existing Structures Inventory & Condition survey report
Appendix-8: Geo Technical Investigation report
Appendix-9: Hydraulic & Hydrological Investigation report
4.3 | Volume-3: Material Report
4.4 | Volume-4: Environmental Assessment Report including Environmental Management Plan (EMP) & Resettlement Action Plan (RAP):
4.5 | Volume-5: Techincal Specification (Special technical specifications which are not covered by MOST Specifications)
4.6 | Volume-6: Rate Analysis
4.7 | Volume-7: Detailed Estimate
4.8 | Volume-8: BOQ
4.9 | Volume-9: Drawings
Part-1 : Highway : Keyplan, Index, Hori. & Vert. Curve Table, LSR, Centreline Coordinate, TBM List, Lane configuration/TCS Schedule, Typical cross sections, Plan-Profile, Road furniture plan, Junction improvement Drawing etc….
Part-2 : Structure : GADs, Protection work (Retaining wall/Toe wall/Gabion/Breast wall, Crash barrier etc….
Part-3 : Project Facility : Toll Plazas, Rest Area, Bus bays, Truck lay buys etc....
4.1 | Volume-10: Drainage Design Report
Appendix-10: Drainage plan
5 | Bid documents and civil works contract agreement along with technical schedules
6 | LA & Clearance II Report
6.1 | ▪ Volume-I : LA II Report
6.2 | Appendix-1: 3(A) & 3(D) Gazzete Notification OR Publication of Section 10A, 11 & 19
6.3 | Appendix-2: Final Strip Plan / LA Plan
6.4 | Appendix-3: Final Estimated cost of Land Acquisition
6.5 | ▪ Volume-II: Utility II Report
6.6 | Appendix-1: Submission of Utility Shifting Estimates
6.7 | Appendix-2: Final Utility Shifting plan with Detailed Utility statement
6.8 | Appendix-3: NO Upgradation Certificate
6.9 | ▪ Volume-III: Clearance II Report
6.1 | Appendix-1: Submission of Final clearances Documents/Drawings received by competent authority
7 | LA & Clearance III Report / Award Determination Report
8 | LA & Clearance IV Report / Land Possession Report